## Design Project Execution
Fixture Stage Tracking Report
Project No |  |  |  | Project Name |  |  |  | Customer Name |  |  |  | Plant |  |  |  | Project Leader |  |  |  | Team Lead
Stage Tracking Register
FIXTURE INFORMATION | [6 empty] | CONCEPT | [5 empty] | DAP | [5 empty] | 3D FINISH |  |  |  |  | 2D FINISH |  |  |  |  | HOLD HISTORY |  |  |  | WORK PROOF REGISTER |  |  |  | SUMMARY
Sr | Fixture No | OP | Part Name | Priority | Assigned | Global | Hrs | Date | Progress | Revisions | Employee | Approval & Status | Hrs | Date | Progress | Revisions | Employee | Approval & Status | Hrs | Date | Progress | Employee | Approval & Status | Hrs | Date | Progress | Rev | Approval & Status | Concept | DAP | 3D | 2D | Concept | DAP | 3D | 2D | Planned | Actual
No |  | No |  |  |  | Status |  | Range | % |  | Name |  |  | Range | % |  | Name |  |  | Range | % | Name |  |  | Range | % | [6 empty] | Proof | Proof | Proof | Proof | Hrs | Hrs
1 | PARC26001301 | OP 10 | Sub Assy Robotic MIG Welding Fixture 01 | high | MANGESH GITE | In Progress |  | 15/05/26 | 100% | CON 00 | MANGESH GITE | IN_PROGRESS |  |  | 0% | DAP 00 |  | PENDING |  |  | 0% |  | PENDING |  |  | 0% | DET 00 | PENDING
2 | PARC26001302 | OP 20 | Sub Assy Robotic MIG Welding Fixture 02 | high | MANGESH GITE | In Progress |  | 15/05/26 | 50% | CON 00 | MANGESH GITE | IN_PROGRESS |  |  | 0% | DAP 00 |  | PENDING |  |  | 0% |  | PENDING |  |  | 0% | DET 00 | PENDING
3 | PARC26001303 | OP 30 | Sub Assy Robotic MIG Welding Fixture 03 | high | MANGESH GITE | In Progress |  | 15/05/26 | 50% | CON 00 | MANGESH GITE | IN_PROGRESS |  |  | 0% | DAP 00 |  | PENDING |  |  | 0% |  | PENDING |  |  | 0% | DET 00 | PENDING
4 | PARC26001304 | OP 40 | Sub Assy Robotic MIG Welding Fixture 04 | high | MANGESH GITE | In Progress |  | 15/05/26 | 50% | CON 00 | MANGESH GITE | IN_PROGRESS |  |  | 0% | DAP 00 |  | PENDING |  |  | 0% |  | PENDING |  |  | 0% | DET 00 | PENDING
5 | PARC26001305 | OP 50 | Sub Assy Robotic MIG Welding Fixture 05 | critical | SHIVAM DESAI | Overdue | 0h 1m | 15/05/26 - 15/05/26 | 100% | CON 00 | SHIVAM DESAI | APPROVED |  |  | 0% | DAP 00 |  | PENDING |  |  | 0% |  | PENDING |  |  | 0% | DET 00 | PENDING | [9 empty] | 0h 1m
6 | PARC26001306 | OP 60 | Sub Assy Inspection Gauge | high | MANGESH GITE | Review |  | 15/05/26 | 50% | CON 00 | MANGESH GITE | IN_PROGRESS |  |  | 0% | DAP 00 |  | PENDING |  |  | 0% |  | PENDING |  |  | 0% | DET 00 | PENDING |  |  |  |  | /uploads/task-proofs/1778852769541-8029776a-10be-4806-b38d-92991a4f0bef.png /uploads/task-proofs/1778852769541-8029776a-10be-4806-b38d-92991a4f0bef.png |  |  |  |  | 0h 5m
7 | PARC26001307 | OP 70 | sub asm-01 | high | MOTILAL KURMI | In Progress |  | 15/05/26 | 50% | CON 00 | MOTILAL KURMI | IN_PROGRESS |  |  | 0% | DAP 00 |  | PENDING |  |  | 0% |  | PENDING |  |  | 0% | DET 00 | PENDING
8 | PARC26001308 | OP 80 | Cradle Asm-01 | high | SHIVAM DESAI | In Progress |  | 15/05/26 | 50% | CON 00 | SHIVAM DESAI | IN_PROGRESS |  |  | 0% | DAP 00 |  | PENDING |  |  | 0% |  | PENDING |  |  | 0% | DET 00 | PENDING
9 | PARC26001309 | OP 90 | Cradle Asm-02 | high | SHIVAM DESAI | In Progress |  | 15/05/26 | 50% | CON 00 | SHIVAM DESAI | IN_PROGRESS |  |  | 0% | DAP 00 |  | PENDING |  |  | 0% |  | PENDING |  |  | 0% | DET 00 | PENDING
10 | PARC26001310 | OP 100 | Cradle Asm-Inspection Gauge | high | MAYURESH SHINGARE | In Progress |  | 15/05/26 | 50% | CON 00 | MAYURESH SHINGARE | IN_PROGRESS |  |  | 0% | DAP 00 |  | PENDING |  |  | 0% |  | PENDING |  |  | 0% | DET 00 | PENDING | 18/05/26 07:17 - MAYURESH SHINGARE
11 | PARC26001311 | OP 110 | TIG welding SPM modification | high | MAYURESH SHINGARE | In Progress |  | 15/05/26 | 50% | CON 00 | MAYURESH SHINGARE | IN_PROGRESS |  |  | 0% | DAP 00 |  | PENDING |  |  | 0% |  | PENDING |  |  | 0% | DET 00 | PENDING